## Schedule - Graph
CHEVERLY - GRANT SCHEDULE
QUARTER | TASK | 2024 |  |  |  | 2025 | [11 empty] | 2026 | [11 empty] | 2027
|  | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept
Q1: September - December 2024 | Notice to Proceed | bar: 2024 Sept
Q2: January to March 2025 | Procurement, Agreements - MDEM Kickoff | bar: 2024 Oct to 2025 May
Q3: April to June 2025 | Concept Design | bar: 2025 June to 2025 Aug
Q4: July to September 2025 | Watershed Analysis - H/H Modeling | bar: 2025 June to 2025 Aug
Survey, Utility Designation | bar: 2025 Aug to 2025 Nov
Q5: October to December 2025 | Preliminary Design | bar: 2025 Oct to 2026 Jan
Q6: January to March 2026 | Nature Based Hazard Mitigation (Outreach); Additional Field Investigations | bar: 2026 Jan to 2026 Mar
Submission (30%) | bar: 2026 Mar
Q7: April to June 2026 | 65% Design and Site Scale NBS Recommendations | bar: 2026 Apr to 2026 July
Q8: July to September 2026 | Submission (65%) to review agencies | bar: 2026 July to 2026 Oct
Q9: October to December 2026 | Review (External Agencies) | bar: 2026 Oct
Additional Outreach | bar: 2026 Oct to 2026 Dec
Q10: January to March 2027 | Final Design (100%) | bar: 2027 Jan to 2027 Mar
Q11: April to June 2027 | Permitting | bar: 2027 Mar to 2027 Aug
Q12: July to September 2027 | Closeout | bar: 2027 Sept
|  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q5 |  |  | Q6 |  |  | Q7 |  |  | Q8 |  |  | Q9 |  |  | Q10 |  |  | Q11 |  |  | Q12
Deliverables
Alternative analysis
PowerPoint Presentation - Outline alternatives for review.
Hydrology modeling - Preliminary
Memo (pdf format)
PC SWM Models (Digital)
Concept design (30%)
Design Plans (30%)
E&SC Plans (30%)
Design Report (digital files only, no hard copies required) - delivered via SharePoint or DropBox (other equivalent file transfer platform)
Nature Based Hazard Mitigation - Site location maps and identification of practices (e.g., forest mgmt., outfalls, naturalized areas, site scale) with benefit analysis (Digital format, PDF)
Semifinal (65%)
Design plans (65%)
E&SC PLANS
Design Report (digital files only, no hard copies required) - delivered via SharePoint or DropBox (other equivalent file transfer platform)
NBS - Community Outreach - Summary of events and meetings (Digital submission - PDF format)
NBS opportunities - Parcel Maps with engagement letters and specific practices applied to individual home to solve individual home flooding (Memo Format - Site Maps and letters - PDF Format)
Final design (100%)
Design plans (100%)
E&SC (100%)
Design Report (digital files only, no hard copies required) - delivered via SharePoint or DropBox (other equivalent file transfer platform)
NBS opportunities - Final documentation with homeowner signed agreements
Utility Designations
CAD Files
PDF’s
Memo (digital files only, no hard copies required) - delivered via SharePoint or DropBox (other equivalent file transfer platform)
Geotechnical investigations
CAD or GIS Files
PDF’s
Report (digital files only, no hard copies required) - delivered via SharePoint or DropBox (other equivalent file transfer platform)
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Council Meetings: March 27, April 10 Award - Schedule March 26 Could it be completed in time for March 27th work session (council typically does not vote but could).

## Scope Grant - Notes
At the project’s initiation, the Town will take the necessary steps to participating jurisdiction in the County Hazard Mitigation Plan. To better understand the Towns flood risk and plan for The Town will then focus its efforts on gaining a better understanding of the flood hazards within the Towns three main watersheds that encompass the areas where the greatest amount of flooding has occurred, as well as the Town itself, evaluate flood vulnerabilities for various precipitation events, identify mitigation opportunities, and prepare construction-ready plans for future mitigation strategies. 1. MDEM Kickoff. Conduct MDEM kick-off within first three months of project initiation. 2. Multi-Jurisdictional Hazard Mitigation Plan. - DELETED 3. Watershed Analysis. Prepare a watershed analysis and collect data. The work will be broken into the following plan sets: 1) Parkway Main Line, 2) Parkway Place Lateral, 3) Cheverly Avenue (West) Lateral, and 4) Cheverly Avenue (East) Lateral (which includes 64th Avenue, Forest Road, Parkway Lateral, and Montrose Main Line). Advise the community about the upcoming analysis. Engage other agencies (water, sewer, etc.) whose work may cause/impact flooding to ID opportunities for coordination, cost sharing, or modifying the approaches. 4. Nature Based Hazard Mitigation. Work with community to explore options for NBS at community and site scale (e.g., forest mgmt., outfalls, naturalized areas, site scale). Identify and implement ways to measure benefits. 5. Concept Design (30%). Prepare 30%, including H&H, drainage/SWM Reports, and E&S designs & calculations. Perform BCA using detailed estimates. Conduct soil/SWM borings, video pipe inspections (jet vac pipes prior), and storm drain structure inventory, utility designations, and groundwater investigations. Solicit community input. 6. Semi- Final (65%) and Site Scale NBS Recommendations. Repeat design steps for 65%. In addition, geotechnical investigations and environmental permitting (JPA/NRI as applicable) submission packages will be prepared. Update BCA. ID site-scale NBS opportunities for interested property owners. Engage community to ID opportunities to resolve localized flooding problems at the neighborhood and individual level. 7. Final Design (95%). Repeat design steps for 95%, updated based on review comments. Resubmit environmental permitting submission packages. Prepare minor local relocation utility designs, as applicable. Prepare metes and bounds descriptions of proposed easements (assumes 10-12 easements). 8. Permitted Plans. Prepare final permitted plan sets, construction cost estimates, and BCA. 9: Sub-Recipient Management. Perform sub-recipient grant management. Prepare and submit quarterly financial and programmatic reports and closeout reporting after POP ends. Initiate MDEM close out two months before project end date.

## Line Items
JET VAC SERVICES AND STORM DRAIN VIDEO INSEPCTIONS WITH MAPPING
Item # | Description | Unit
1 | 8-hours of Inlet Cleaning (2-person crew at normal hours) | Daily
2 | High pressure Pipe Cleaning (2-person crew at normal hours) | Daily
3 | Video Inspection (DVD) of Pipe System (2-person crew at normal hours) | Daily
4 | CCTV Inspection of Storm Drains
4.a | Up to 8-inch pipe | LF
4.b | 8-inch to 12-inch pipe | LF
4.c | 13 to 36-inch pipe | LF
4.d | 37-inch to 72-inch pipe | LF
4.e | Minimum daily project charge for CCTV inspection | Daily

## Timeline
Tasks
Start | End | Duration | Label | Vert. Position | Vert. Line
2024-09-10 | 2024-12-31 |  | Notice to Proceed, Procurement | -25 | -25
2025-01-01 | 2025-03-31 |  | Procurement, Kickoff | -40 | -40
2025-04-01 | 2025-06-30 |  | Concept Design | -55 | -55
2025-07-01 | 2025-09-30 |  | Field, H/H Modeling | -80 | -80
2025-10-01 | 2025-12-31 |  | H/H Modeling, Preliminary Design | -25 | -25
2026-01-01 | 2026-03-31 |  | Submission, Outreach, Additional Field | -40 | -40
2026-04-01 | 2026-06-30 |  | 65% Design | -55 | -55
2026-07-01 | 2026-09-30 |  | Submission to review agencies | -80 | -80
2026-10-01 | 2026-12-31 |  | Review, Additional Outreach | -25 | -25
2027-01-01 | 2027-03-31 |  | Final Design (100%) | -40 | -40
2027-04-01 | 2027-06-30 |  | Permitting | -55 | -55
2027-07-01 | 2027-09-11 |  | Closeout | -80 | -80
Insert new rows above this one
Milestones
Date |  |  | Label | Position
2024-09-10 |  |  | Notice to Proceed | 5
2024-12-31 |  |  | Milestone #1 | 10 | Q1: September - December 2024
2025-03-31 |  |  | Milestone #2 | 15 | Q2: January to March 2025
2025-06-30 |  |  | Milestone #3 | 20 | Q3: April to June 2025
2025-09-30 |  |  | Milestone #4 | 25 | Q4: July to September 2025
2025-12-31 |  |  | Milestone #5 | 5 | Q5: October to December 2025
2026-03-31 |  |  | Milestone #6 | 10 | Q6: January to March 2026
2026-06-30 |  |  | Milestone #7 | 15 | Q7: April to June 2026
2026-09-30 |  |  | Milestone #8 | 20 | Q8: July to September 2026
2026-12-31 |  |  | Milestone #9 | 5 | Q9: October to December 2026
2027-03-31 |  |  | Milestone #10 | 10 | Q10: January to March 2027
2027-06-30 |  |  | Milestone #11 | 15 | Q11: April to June 2027
2027-09-11 |  |  | Milestone #12 | 20 | Q12: July to September 2027
2027-09-11 |  |  | Project End Date | 25
Insert new rows above this one
Formulas:
Start = [End, row above]+1

## About
PROJECT TIMELINE by Vertex42.com
https://www.vertex42.com/ExcelTemplates/project-timeline.html
About This Template
This template uses a scatter chart with data labels and error bars to create a project timeline that shows both milestones and tasks with durations. Unlike a Gantt chart, which shows each task on a separate row, you control the vertical positioning of tasks within the timeline. You can specify the length of the vertical leader line to help show task dependencies.
This type of project timeline is mainly useful for a general overview of a project rather than showing a detailed work breakdown structure.
More Templates
Visit Vertex42.com to download other timeline and project management templates.
More Timeline Templates
More Project Management Templates
About Vertex42
Vertex42.com provides professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.